# Kaupapa Māori Budget Planning Template

A practical tool to support whānau and hāpori to forecast the true cost of delivering each adaptation response.

- Guides the rōpū to break each response down into step-by-step components such as labour, materials, coordination, and technical support.

- Encourages gathering quotes from trusted local contractors, tangata whenua providers, and specialists.

- Promoting locally sourced solutions and invests in building tangata whenua capability and capacity.

A Strategic Budgeting Tool to Support Tangata Whenua-led Climate Adaptation Responses

### Purpose and Function

This template supports tangata whenua to prepare comprehensive, transparent, and funder-ready budgets for each adaptation response identified in your plan. It ensures all costs are realistic, culturally grounded, and fully scoped by:

- Breaking each kaupapa into logical delivery components

- Forecasting true costs (labour, materials, technical, logistics, etc.)

- Promoting procurement from local and tangata whenua suppliers

- Aligning budget decisions with kaupapa Māori values

- Supporting robust funding proposals and pūtea mobilisation

## Section 1: Budget Forecast Table (template)

| Adaptation Response | The title of the specific project or action (e.g. "Puna Restoration at Lake Kaiiwi") |
| --- | --- |

### Budget Breakdown Table

| Description of Task / Activity | Estimated Quantity or Duration | Cost ($) | Supplier / Provider Name | Required Attachment (Appendix #) | Notes / Dependencies |
| --- | --- | --- | --- | --- | --- |
| Technical assessment and soil testing | 2 days | $600/day | Manaaki Earthworks | Appendix 21-A: Quote from Manaaki Earthworks | Required before design work begins |
| Planting by rangatahi rōpū over 3 days | 3 days x 4 people | $350/day/person | Kōkiri Taiao Trust | Appendix 21-B: Rōpū Scope + Timesheet Draft | Links to Appendix 8: Project Plan |
| Purchase of native riparian species | 400 plants | $5 per plant | Te Rito Native Nursery | Appendix 21-C: Supplier Invoice / Quote | Ensure eco-sourced only |
| Community-based part-time support | 1 person, 4 wks @ 10hrs/wk | $40/hr | Internal | Appendix 21-D: Role Description | Consider long-term coordination |
| On-site tangata whenua oversight during works | 2 days | $600/day | Te Waiariki Kaitiaki Collective | Appendix 21-E: Kaitiaki Role Description | Aligns with Appendix 16: Atua Risk Observations |

### Total: $_________

### (Ensure GST, inflation margins, contingency, and volunteer/koha contributions are noted where relevant)

| Adaptation Response Name | The title of the specific project or action (e.g. Flood Protection) |
| --- | --- |

### Budget Breakdown Table

| Task / Activity | Detailed Description | Estimated Quantity / Duration | Total Cost ($) | Supplier / Provider | Notes / Dependencies |
| --- | --- | --- | --- | --- | --- |
| Site Assessment and Planning | Initial technical assessment, site mapping, soil testing | 3 days | $1,500 | Manaaki Earthworks Ltd | Required before design phase |
| Engineering Design | Development of technical drawings and specifications | 1 plan set | $2,000 | WhenuaSafe Ltd | Includes peer review |
| Resource Consent Application | Preparation and lodgement of consent with Council | 1 application | $1,200 | Local Planning Services | May incur additional Council fees |
| Labour – Wall Construction | 4-person crew for 5 days @ $400/day/person | 20 days | $8,000 | Kōkiri Builders Co-op | Local employment opportunity |
| Materials – Gabion Baskets, Gravel, Geotextile | Based on design specs | 1 bulk order | $5,500 | Kāinga Supplies | Confirm freight charges |
| Cultural Monitoring | Tangata whenua monitor onsite during earthworks | 3 days | $1,800 | Te Rūnanga o Ngati x | Ensure tikanga compliance |
| Project Coordination | Part-time coordination support over 2 months | 40 hrs | $2,000 | Internal rōpū coordinat | Oversees delivery timeline |
| Post-Project Maintenance | Quarterly site checks and touch-ups | 4 visits | $1,000 | TBC | Review 12 months post-completion |

### Total: $_________

### (Ensure GST, inflation margins, contingency, and volunteer/koha contributions are noted where relevant)

| Adaptation Response Name | The title of the specific project or action (e.g. Flood Protection) |
| --- | --- |

### Budget Breakdown Table

| Task / Activity | Detailed Description | Estimated Quantity / Duration | Total Cost ($) | Supplier / Provider | Notes / Dependencies |
| --- | --- | --- | --- | --- | --- |

### Subtotal: $_________

### (Ensure GST, inflation margins, contingency, and volunteer/koha contributions are noted where relevant)

### Instructions for Use

Based on the examples provided in the table below, please complete a separate Budget Forecast Table for each adaptation response identified in your Kaupapa Māori Climate Adaptation Plan (Step 2.4).

For each adaptation response:

- Break the kaupapa into clear, step-by-step tasks or activities.

- Provide detailed descriptions of what each task involves.

- Estimate the quantity, duration, unit cost, and total cost for each component.

- Identify the supplier or provider and indicate whether they are a local or tangata whenua provider.

- Attach supporting documentation such as quotes, scopes of work, or supplier profiles, and reference these as appendices.

- Include any notes, dependencies, or links to other tools (e.g. project plans, role descriptions).

This process ensures all costs are transparent, realistic, and culturally grounded, and that local procurement, whānau employment, and kaupapa Māori delivery are prioritised. Use this as the foundation for funding applications, implementation planning, and Council engagement.

## Section 2: Required Attachments and Appendices

To ensure transparency, clarity, and cultural alignment, please include the following appendices alongside your budget table:

| Appendix | Attachment Type | Purpose | Required Content |
| --- | --- | --- | --- |
| A | Quote from contractors/suppliers | Verifies actual cost estimates | Dated quote, contact details, GST status |
| B | Scope of mahi / Role outlines | Clarifies tasks and costs | Deliverables, timeframe, hourly/daily rate |
| C | Materials lists or product invoices | Validates materials or equipment costs | Quantity breakdown, supplier source, eco-certification (if relevant) |
| D | Evidence of local provider or whānau-led delivery | Demonstrates commitment to kaupapa Māori procurement | Brief profile, rohe connection, or previous mahi |
| E | Cultural considerations or tikanga-based roles | Validates inclusion of tangata whenua-specific expertise | Role description, responsibilities, koha or wage |
| F | Summary of budget assumptions | Clarifies costing rationale | Justification for costs, inflation buffer, contingency margins |

## Section 3: Budget Review Checklist

| ✅ | Budget Quality Indicators |
| --- | --- |
| ☐ | Budget is broken down into clear and achievable stages or tasks |
| ☐ | All quotes are from trusted, ideally local or tangata whenua suppliers |
| ☐ | Budget reflects tikanga-based roles and cultural monitoring as legitimate project costs |
| ☐ | Budget supports whānau, rangatahi, and local economic participation |
| ☐ | Budget is linked to the Project Plan (Appendix 8) and aligns with Adaptation Responses (Step 2.4) |
| ☐ | Koha, facilitation, hauora support, and admin time are fairly valued |
| ☐ | Contingency fund (5–15%) is included for unexpected changes |
| ☐ | Appendices are complete, labelled, and professionally presented |

## Section 4: Cultural Integrity Notes

To uphold a tika and pono  budgeting processes:

- Do not undervalue unpaid whānau labour, kaumātua time, or kaupapa-specific roles.

- Ensure koha and tikanga-led roles (e.g. kai karanga, kaitiaki, tohunga) are reflected in the pūtea.

- Embed manaakitanga (e.g. kai, hauora support, transport) into project costs.

- View budgeting as an extension of kaitiakitanga, caring for the kaupapa and the people.